## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Distance Learning Camera Plan | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Arizona Western College | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Robert Schroeder |  | Project Start Date: |  | 8/3/202
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | July | [13 empty] | August | [27 empty] | September
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-07-24 to 2020-09-17
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Aquire Camera Systems |  | Adriana P.
| Aquire Camera Systems From Vendor | Milestone | Adriana P. | 0% | 2020-08-05 | 1 | bar: W
| Asset Input Into Wasp | Goal | Adriana P. | 0% | 2020-08-05 | 1 | W: 2
| Transfer Cameras To SD | Goal | SD Tech 1 | 0% | 2020-08-05 | 1 | W: 2
| Camera Deployment (Priority Rooms) |  | Robert S.
| LA 116 | High Risk | SD Tech 1 | 0% | 2020-08-05 | 1
| SC 210 | High Risk | SD Tech 1 | 0% | 2020-08-05 | 1
| BA 225 | High Risk | Sd Tech 1 | 0% | 2020-08-05 | 1
| SLTI1 | High Risk | Victor M. | 0% | 2020-08-05 | 1
| Camera Deployment (Yuma Campus) |  | Robert S.
| AC Bldg (6) | On Track | SD Tech 2 |  | 2020-08-11 | 1
| AL Bldg (1) | On Track | SD Tech 2 |  | 2020-08-13 | 1
| AS Bldg (12) | On Track | SD Tech 1 |  | 2020-08-06 | 1
| BA Bldg (9) | On Track | SD Tech 2 |  | 2020-08-12 | 1
| EB Bldg (1) | On Track | SD Tech 2 |  | 2020-08-12 | 1
| ES Bldg (3) | On Track | SD Tech 2 |  | 2020-08-12 | 1
| GY Bldg (2) | On Track | SD Tech 1 |  | 2020-08-06 | 1
| LA Bldg (8) | On Track | SD Tech 2 |  | 2020-08-11 | 1
| LR Bldg (12) | On Track | SD Tech 2 |  | 2020-08-10 | 1
| PSI Bldg (2) | On Track | SD Tech 2 |  | 2020-08-10 | 1
| SC Bldg (6) | On Track | SD Tech 2 |  | 2020-08-13 | 1
| T4 Bldg (1) | On Track | SD Tech 2 |  | 2020-08-13 | 1
| Camera Deployment (Other Campuses) |  | Victor M.
| SLLC (10) | On Track | Victor M. | 0% | 2020-08-06 | 8
| SLTI (8) | On Track | Victor M. |  | 2020-08-06 | 8
| Somerton (9) | On Track | Victor M. |  | 2020-08-06 | 8
| Downtown Center (5) | On Track | Victor M. |  | 2020-08-06 | 8
| Parker (3) | On Track | Victor M. |  | 2020-08-06 | 8
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## Yuma Campus - Classrooms
Building | Classroom | Complete
AC | 159
AC | 279
AC | 282
AC | 286
AC | 288
AC | 289
AL | 101
AS | 101
AS | 110
AS | 112
AS | 113
AS | 114
AS | 115
AS | 202
AS | 206
AS | 207
AS | 209
AS | 210
AS | 215
BA | 101
BA | 111
BA | 118
BA | 119
BA | 124
BA | 201
BA | 205
BA | 225
BA | 230
EB | 127
ES | 105
ES | 107
ES | 112
GY | 108
GY | 116
LA | 105
LA | 106
LA | 107
LA | 108
LA | 114
LA | 115
LA | 116
LA | 117
LR | 46
LR | 47
LR | 50
LR | 53
LR | 96
LR | 97
LR | 98
LR | 101
LR | 104
LR | 106
LR | 250
LR | 251
PSI | 112
PSI | 113
SC | 117
SC | 118
SC | 119
SC | 120
SC | 210
SC | 212
T4 | 113